CVP 613 Mentoring Action Plan Worksheet*

Creating a Mentoring Action plan assists mentors and mentees to work together to create a framework for their mentoring relationship and the perfusion Capstone project.

Step 1: Define the goal the mentee/Capstone group hopes to achieve by the completion of the semester. Use SMART goals. SMART goals are used to help guide you in setting your goals. SMART is an acronym that stands for Specific, Measurable, Achievable, Realistic, and Timely. A SMART goal incorporates all the following criteria to aid in focusing your efforts and increase the chances of achieving your goal:

- Specific: well-defined, clear, unambiguous

- Measurable: With specific criteria that measure your progress toward the accomplishment of the goal

- Achievable: Attainable and not impossible to achieve

- Realistic: Within reach, realistic, and relevant

- Timely: With a clearly defined timeline, including a starting date and target date

Step 2: Identify strategic actions that help the mentee/mentor reach their goal.

Step 3: For each strategic action:

- Determine the mentee(s) action steps

- Determine the mentor(s) action steps

- Identify potential obstacles and challenges

- Identify needed resources

- Set a timeline for completion

Step 4: Success Metrics: Identify how progress will be measured (e.g., completed tasks, improved skills, increased knowledge).

Step 5: Feedback: Mentee and mentor feedback notes.

Goal #1

Goal #1: Finalize the CPB Perfusion Tool project scope and research question

| Strategic Action | Clarify the Capstone project's purpose, population, measurable outcomes, and final deliverables. |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Finalize the PICOT/research question, define the tool's educational scope, identify the core modules, and align the project with the capstone proposal requirements. | Review the research question, confirm the scope is realistic for the semester, and provide feedback on whether the goals are measurable and achievable. | Scope creep, changing tool features, and difficulty narrowing the project to achievable outcomes. | Capstone rubric, project notes, current web-based tool, mentor feedback, and proposal draft. | July 13-19, 2026 |
| Success Metrics | A finalized research question and written scope statement that identify the target population, intervention, comparison, outcomes, and timeline. |  |  |  |
| Notes & Feedback | This goal keeps the project focused on education, simulation, and planning support rather than clinical decision-making. |  |  |  |

Goal #2

Goal #2: Obtain stakeholder feedback on the web-based CPB Perfusion Tool

| Strategic Action | Gather feedback from perfusion students, instructors, preceptors, and practicing perfusionists about usability, workflow fit, calculations, and educational value. |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Prepare a tool demonstration, develop feedback questions, meet with available stakeholders, and summarize recommendations for tool improvement. | Help identify appropriate stakeholders, review feedback questions, and guide which recommendations should be prioritized. | Scheduling conflicts, limited participant availability, and differing institutional protocols or preferences. | Tool prototype, stakeholder feedback form, capstone mentor, perfusion faculty/preceptors, and current literature. | August 10-23, 2026 |
| Success Metrics | Feedback is collected from relevant stakeholders and summarized into actionable revisions for the tool. |  |  |  |
| Notes & Feedback | Stakeholder input will help determine whether the tool reflects realistic perfusion workflow and learner needs. |  |  |  |

Goal #3

Goal #3: Validate formulas, assumptions, and evidence supporting the tool

| Strategic Action | Confirm that calculations and assumptions used in the perfusion, prime planning, and anticoagulation modules are supported by reliable references and stakeholder review. |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Complete the literature review, update the evidence table, review formulas for BSA, DO2i, flow, hemodilution, heparin, and protamine, and document assumptions clearly. | Review the evidence table, recommend authoritative sources, and verify whether the validation plan is appropriate for an educational tool. | Formula variation across sources, institutional differences, and deciding which assumptions are appropriate for simulation use. | AmSECT standards, STS/SCA/AmSECT guidelines, goal-directed perfusion literature, usability literature, and JHEBP appraisal table. | July 20-August 23, 2026 |
| Success Metrics | A completed evidence table and validation plan with referenced formulas, visible assumptions, and identified limitations. |  |  |  |
| Notes & Feedback | Validation should support safe educational framing and should not imply the tool replaces clinical judgment or institutional protocols. |  |  |  |

Goal #4

Goal #4: Create and use a survey to evaluate cognitive load, usability, and learner confidence

| Strategic Action | Develop data collection tools to determine whether the CPB Perfusion Tool reduces cognitive workload and supports simulation learning. |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Create a survey using SUS items, NASA-TLX or a brief workload rating, confidence questions, and open-ended prompts; prepare instructions for the incoming class after IRB/program approval. | Review survey items for clarity, confirm alignment with the research question, and advise on ethical data collection and interpretation. | IRB timing, small sample size, survey fatigue, and difficulty linking user feedback directly to tool effectiveness. | IRB/program guidance, consent or information sheet, survey platform, simulation case, SUS, NASA-TLX, and mentor feedback. | September 1-November 15, 2026 |
| Success Metrics | Survey is finalized, distributed after approval, and results are summarized for usability, cognitive load, confidence, and improvement priorities. |  |  |  |
| Notes & Feedback | Data will be de-identified and used to guide revisions to the educational tool. |  |  |  |

Goal #5

| Strategic Action |  |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Success Metrics |  |  |  |  |
| Notes & Feedback |  |  |  |  |

Goal #6

| Strategic Action |  |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Success Metrics |  |  |  |  |
| Notes & Feedback |  |  |  |  |

*Adapted from the American College of Physicians