CVP 613 Mentoring Action Plan Worksheet*

Creating a Mentoring Action plan assists mentors and mentees to work together to create a framework for their mentoring relationship and the perfusion Capstone project.

Step 1: Define the goal the mentee/Capstone group hopes to achieve by the completion of the semester. Use SMART goals. SMART goals are used to help guide you in setting your goals. SMART is an acronym that stands for Specific, Measurable, Achievable, Realistic, and Timely. A SMART goal incorporates all the following criteria to aid in focusing your efforts and increase the chances of achieving your goal:

- Specific: well-defined, clear, unambiguous

- Measurable: With specific criteria that measure your progress toward the accomplishment of the goal

- Achievable: Attainable and not impossible to achieve

- Realistic: Within reach, realistic, and relevant

- Timely: With a clearly defined timeline, including a starting date and target date

Step 2: Identify strategic actions that help the mentee/mentor reach their goal.

Step 3: For each strategic action:

- Determine the mentee(s) action steps

- Determine the mentor(s) action steps

- Identify potential obstacles and challenges

- Identify needed resources

- Set a timeline for completion

Step 4: Success Metrics: Identify how progress will be measured (e.g., completed tasks, improved skills, increased knowledge).

Step 5: Feedback: Mentee and mentor feedback notes.

Goal #1

Goal #1: Finalize the CPB Perfusion Tool project scope and research question

| Strategic Action | Clarify the Capstone project's purpose, population, measurable outcomes, and final deliverables. |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Finalize PICOT question, educational scope, core modules, and proposal alignment. | Review scope, confirm feasibility, and provide feedback on measurable outcomes. | Scope creep, changing features, and narrowing outcomes. | Capstone rubric, project notes, web tool, mentor feedback, proposal draft. | July 13-19, 2026 |
| Success Metrics | Final research question and scope statement identify population, intervention, outcomes, and timeline. |  |  |  |
| Notes & Feedback | This goal keeps the project focused on education, simulation, and planning support rather than clinical decision-making. |  |  |  |

Goal #2

Goal #2: Obtain stakeholder feedback on the web-based CPB Perfusion Tool

| Strategic Action | Gather stakeholder feedback on usability, workflow fit, calculations, and educational value. |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Prepare demo, develop feedback questions, meet with stakeholders, and summarize recommendations. | Identify stakeholders, review questions, and help prioritize recommendations. | Scheduling conflicts, limited availability, and protocol differences. | Tool prototype, stakeholder feedback form, capstone mentor, perfusion faculty/preceptors, and current literature. | August 10-23, 2026 |
| Success Metrics | Stakeholder feedback is summarized into actionable tool revisions. |  |  |  |
| Notes & Feedback | Stakeholder input will help determine whether the tool reflects realistic perfusion workflow and learner needs. |  |  |  |

Goal #3

Goal #3: Validate formulas, assumptions, and evidence supporting the tool

| Strategic Action | Confirm that calculations and assumptions are supported by references and stakeholder review. |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Update literature review, evidence table, formula list, and visible assumptions. | Review evidence table, recommend sources, and confirm validation approach. | Formula variation, institutional differences, and simulation assumptions. | AmSECT standards, STS/SCA/AmSECT guidelines, GDP literature, usability literature, JHEBP table. | July 20-August 23, 2026 |
| Success Metrics | Evidence table and validation plan include referenced formulas, assumptions, and limitations. |  |  |  |
| Notes & Feedback | Validation supports educational framing and does not replace protocols or clinical judgment. |  |  |  |

Goal #4

Goal #4: Create and use a survey to evaluate cognitive load, usability, and learner confidence

| Strategic Action | Develop tools to evaluate cognitive workload, usability, and learner confidence. |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Create survey with SUS, NASA-TLX or workload rating, confidence items, and open-ended prompts. | Review survey clarity, alignment with PICOT question, and ethical data collection. | IRB timing, small sample size, survey fatigue, and attribution limits. | IRB/program guidance, consent or information sheet, survey platform, simulation case, SUS, NASA-TLX. | September 1-November 15, 2026 |
| Success Metrics | Survey is finalized, distributed after approval, and summarized for usability, workload, confidence, and revisions. |  |  |  |
| Notes & Feedback | Data will be de-identified and used to guide revisions to the educational tool. |  |  |  |

Goal #5

| Strategic Action |  |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Success Metrics |  |  |  |  |
| Notes & Feedback |  |  |  |  |

Goal #6

| Strategic Action |  |  |  |  |
| --- | --- | --- | --- | --- |
| Mentee Action Steps | Mentor Action Steps | Potential Challenges/Obstacles | Resources Needed | Projected Date of Completion |
| Success Metrics |  |  |  |  |
| Notes & Feedback |  |  |  |  |

*Adapted from the American College of Physicians